## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of January' 2011
MPR- Part-I
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Register | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals | Avg. No. of Employment Provided per Household | % Women
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C | [25 empty] | Minority |  | Women | bar: 9
1 | 2 |  | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12 | [16 empty] | SC | ST | Others | Total
1 | Alipurduar-I | 39654 | 20965 | 8631 | 10108 | 39704 | 20125 |  | 20028 | 9002 |  | 2.4938 | 0.84109 | 0.69893 | 4.0338 | 1.5392 | 0.14575 | 40 | 1494 | 26 | 20.141 | 38.16% | 38.16% | 20.85% | 0.25665 | 0.02985 | 114.8807 | 100.5629 | 4.0338 | 4.0338 | 0 | 97.8335 | 3.2671 | 0.61822 | 0.20851 | 0.17327 | 2.4938 | 0.84109 | 0.69893 | 4.0338 | 0.98478 | 0.20853 | 0.14575 | 0.38156 | 1.5392 | 0 | 0.22898 | 0.16004 | 0.014289 | 7 | 1269 | 26 | -33 | -225 | 0
2 | Alipurduar-II | 44575 | 19699 | 9478 | 12205 | 41382 | 20737 |  | 20441 | 9827 |  | 1.584 | 0.53076 | 2.1742 | 4.289 | 1.3343 | 0.4534 | 29 | 236 | 29 | 20.9824 | 31.11% | 31.11% | 20.85% | 0.36819 | 0.07645 | 146.1372 | 101.5899 | 2.9528 | 4.289 | 1.3362 | 101.5899 | 4.289 | 0.36932 | 0.12375 | 0.50693 | 1.584 | 0.53076 | 2.1742 | 4.289 | 0.87223 | 0.20853 | 0.4534 | 0.31109 | 1.3343 | 0 | 0.089865 | 0.19539 | -0.25801 | 16 | 256 | 29 | -13 | 20 | 0
3 | Dhupguri | 80508 | 39105 | 16764 | 21163 | 77032 | 42968 |  | 42885 | 9510 |  | 6.8267 | 2.3995 | 3.0871 | 12.3133 | 5.541 | 0.64376 | 38 | 602 | 41 | 28.7123 | 45% | 45% | 20.85% | 1.3983 | 0.18348 | 99.9536 | 100.0593 | 11.595 | 12.3133 | 0.71826 | 100.0593 | 12.3133 | 0.55442 | 0.19487 | 0.25071 | 6.8267 | 2.3995 | 3.0871 | 12.3133 | 2.9887 | 0.20853 | 0.64376 | 0.45 | 5.541 | 0 | 0.21327 | 0.65839 | 0.014631 | 0 | 912 | 41 | -38 | 310 | 0
4 | Falakata | 49083 | 22167 | 9586 | 16396 | 48149 | 21212 |  | 20192 | 7504 |  | 2.0778 | 0.82493 | 1.3611 | 4.2638 | 1.8629 | 0.28383 | 167 | 1746 | 41 | 21.1163 | 43.69% | 43.69% | 20.85% | 0.66264 | 0.08436 | 103.2914 | 102.3292 | 3.8486 | 4.2638 | 0.41523 | 102.3292 | 4.2638 | 0.48731 | 0.19347 | 0.31922 | 2.0778 | 0.82493 | 1.3611 | 4.2638 | 1.2246 | 0.20853 | 0.28383 | 0.43691 | 1.8629 | 0 | 0.12111 | 0.16484 | -0.11899 | 8 | 1500 | 41 | -159 | -246 | 0
5 | Kalchini | 56348 | 8355 | 31072 | 15593 | 55020 | 21014 |  | 20547 | 10828 |  | 0.90082 | 2.3605 | 1.9453 | 5.2067 | 2.1826 | 0.40566 | 16 | 2457 | 17 | 25.3402 | 41.92% | 41.92% | 20.85% | 0.25807 | 0.04575 | 123.0278 | 100.7899 | 4.3531 | 5.2067 | 0.85353 | 100.7899 | 5.2067 | 0.17301 | 0.45337 | 0.37362 | 0.90082 | 2.3605 | 1.9453 | 5.2067 | 1.4922 | 0.20853 | 0.40566 | 0.4192 | 2.1826 | 0 | 0.044626 | 0.086812 | -0.31885 | 0 | 2157 | 17 | -16 | -300 | 0
6 | Kumargram | 39869 | 15435 | 13492 | 9346 | 38273 | 30415 |  | 30072 | 9872 |  | 2.3559 | 3.5338 | 1.9632 | 7.8529 | 3.5338 | 0.40939 | 6 | 5126 | 278 | 26.1136 | 45% | 45% | 20.85% | 1.0794 | 0.12505 | 81 | 99.252 | 7.8529 | 7.8529 | 0 | 86.3088 | 6.626 | 0.3 | 0.45 | 0.25 | 2.3559 | 3.5338 | 1.9632 | 7.8529 | 2.4868 | 0.20853 | 0.40939 | 0.45 | 3.5338 | 0 | 0.26335 | 0.51701 | 0.10762 | 0 | 5126 | 278 | -6 | 0 | 0
7 | Madarihat-Birpara | 38645 | 7774 | 16308 | 14225 | 38307 | 22719 |  | 21362 | 5305 |  | 1.2942 | 2.4528 | 2.3342 | 6.0812 | 3.2499 | 0.48675 | 3 | 74 | 127 | 28.4675 | 53.44% | 53.44% | 20.85% | 0.36946 | 0.04223 | 80.1581 | 100.4944 | 6.0812 | 6.0812 | 0 | 84.7071 | 4.8802 | 0.21282 | 0.40335 | 0.38383 | 1.2942 | 2.4528 | 2.3342 | 6.0812 | 1.9789 | 0.20853 | 0.48675 | 0.53442 | 3.2499 | 0 | 0.19583 | 0.45709 | -0.029655 | 22 | 201 | 127 | 19 | 127 | 0
8 | Mal | 57213 | 18393 | 20598 | 18221 | 57212 | 20679 |  | 20321 | 7116 |  | 1.9166 | 1.6922 | 1.9582 | 5.5671 | 2.3404 | 0.40835 | 38 | 527 | 71 | 27.3956 | 42.04% | 42.04% | 20.85% | 0.31873 | 0.04705 | 116.1972 | 98.1499 | 4.0657 | 5.5671 | 1.5013 | 98.1499 | 5.5671 | 0.34428 | 0.30397 | 0.35175 | 1.9166 | 1.6922 | 1.9582 | 5.5671 | 1.7092 | 0.20853 | 0.40835 | 0.4204 | 2.3404 | 0 | 0.18407 | 0.36044 | -0.047906 | 0 | 527 | 71 | -38 | 0 | 0
9 | Matiali | 24986 | 5985 | 12135 | 6226 | 24346 | 13860 |  | 13482 | 3322 |  | 0.71894 | 1.3423 | 0.58914 | 2.6504 | 1.3837 | 0.12286 | 16 | 216 | 94 | 19.6585 | 52.21% | 52.21% | 20.85% | 0.36567 | 0.02349 | 99.6517 | 101.0225 | 2.5694 | 2.6504 | 0.080925 | 101.0225 | 2.6504 | 0.27126 | 0.50645 | 0.22229 | 0.71894 | 1.3423 | 0.58914 | 2.6504 | 0.99313 | 0.20853 | 0.12286 | 0.52207 | 1.3837 | 0 | 0.19181 | 0.113 | -0.0098546 | 0 | 204 | 94 | -16 | -12 | 0
10 | Maynaguri | 67180 | 49852 | 1048 | 14866 | 65766 | 36998 |  | 36221 | 1181 |  | 5.6041 | 0.13474 | 1.5242 | 7.263 | 4.7795 | 0.31784 | 19 | 1153 | 73 | 20.052 | 65.81% | 65.81% | 20.85% | 1.5372 | 0.0653 | 124.1776 | 99.2579 | 6.6707 | 7.263 | 0.59233 | 99.2579 | 7.263 | 0.7716 | 0.018551 | 0.20985 | 5.6041 | 0.13474 | 1.5242 | 7.263 | 1.7581 | 0.20853 | 0.31784 | 0.65805 | 4.7795 | 0 | 0.1202 | 0.18321 | -0.13463 | 5 | 1066 | 73 | -14 | -87 | 0
11 | Nagrakata | 25551 | 3981 | 14866 | 6669 | 25516 | 16258 |  | 16387 | 2086 |  | 0.29381 | 1.056 | 0.50564 | 1.8554 | 0.63464 | 0.10544 | 13 | 52 | 16 | 11.3226 | 34.2% |  |  | 0 | 0 | 98.417 | 99.1169 | 1.8554 | 1.8554 | 0 | 86.6238 | 1.5926 | 0.15835 | 0.56913 | 0.27252 | 0.29381 | 1.056 | 0.50564 | 1.8554 | 0.51953 | 0.20853 | 0.10544 | 0.34204 | 0.63464 | 0 | 0.196 | 0.099106 | -0.0063371 | 0 | 68 | 16 | -13 | 16 | 0
12 | Rajganj | 50740 | 29823 | 2726 | 17511 | 50060 | 15420 |  | 15322 | 6478 |  | 1.5402 | 0.36727 | 0.89724 | 2.8047 | 1.1501 | 0.1871 | 7 | 1085 | 16 | 18.3049 | 41.01% | 41.01% | 20.85% | 0.15819 | 0.09394 | 101.7596 | 100.4488 | 2.6645 | 2.8047 | 0.14013 | 100.4488 | 2.8047 | 0.54914 | 0.13095 | 0.31991 | 1.5402 | 0.36727 | 0.89724 | 2.8047 | 0.87933 | 0.20853 | 0.1871 | 0.41007 | 1.1501 | 0 | 0.47593 | 0.42702 | 0.23992 | 3 | 1012 | 16 | -4 | -73 | 0
13 | Sadar | 59423 | 36995 | 4458 | 17558 | 59011 | 24144 |  | 23395 | 8208 |  | 1.8983 | 0.10567 | 1.0791 | 3.083 | 1.0164 | 0.22502 | 12 | 830 | 95 | 13.1781 | 32.97% | 32.97% | 20.85% | 0.0711 | 0.03738 | 142.243 | 113.5153 | 3.083 | 3.083 | 0 | 97.411 | 1.9433 | 0.61572 | 0.034275 | 0.35 | 1.8983 | 0.10567 | 1.0791 | 3.083 | 0.53216 | 0.20853 | 0.22502 | 0.32967 | 1.0164 | 0 | 0.3039 | 0.32793 | 0.1029 | 1 | 653 | 95 | -11 | -177 | 0
| Total: | 633775 | 278529 | 161162 | 180087 | 619778 | 306549 | 0 | 300655 | 90239 | 0 | 29.5052 | 17.6417 | 20.1174 | 67.2643 | 30.5483 | 4.1952 | 404 | 15598 | 924 | 22.3726 | 45.42% | [5 empty] | 96.5482 |  | 67.2643
|  |  | 213245 | 101708 | 317233 | 632186 | 4: 300656; 5: 2.813; 6: 23.9119 |  |  | 13.7872 | [5 empty] | 57658.3731 | 0
[6 empty] | 12408 | 4: 3.0066; 5: 22.3725
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2010-11 Up to the Month of January' 2011
Jalpaiguri District | [14 empty] | (Rs. in lakh)
Sl. No. | Name of the Block | Actual O.B. as on 01.04.10 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12) | Balance |  | Expenditure up to prev. months | expenditure during the month | Balance | Balance | Balance
[13 empty] | Recurring | Non-Recurring
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | 55.1042 |  |  | 629.9044 |  |  | 685.0086 |  | 394.6436 | 17.3083 | 125.3807 | 53.6013 | 8.444 | 599.3779 | 85.6307 | 97.8335 | 274.4036 | 324.9743 | 61.85 |  | 186.4763 | 77.3267 | 0.063856 | 594.9652 | 574.4589 | 599.3779 | 24.919 | 438.0416 | 161.3363 | 0.65842 | 0.028877 | 0.20918 | 0.089428 | 0.014088 | 394.6436 | 17.3083 | 125.3807 | 53.6013 | 8.444 | 599.3779
2 | Alipurduar-II | 27.1426 |  |  | 634.4561 |  |  | 661.5986 |  | 435.7216 | 8.1949 | 129.3627 | 16.238 | 0.19275 | 589.7099 | 71.8887 | 101.59 | 304.4107 | 285.2992 | 36.8577 |  | -9.028 | -8.386 | 0.062826 | 589.7099 | 470.1956 | 589.7099 | 119.5143 | 392.2321 | 197.4779 | 0.73887 | 0.013896 | 0.21937 | 0.027536 | 0.00032686 | 435.7216 | 8.1949 | 129.3627 | 16.238 | 0.19275 | 589.7099
3 | Dhupguri | 55.2121 |  |  | 2064.5513 |  |  | 2119.7634 |  | 1232.0571 | 100.0733 | 489.713 | 21.2918 | 35.9916 | 1879.1267 | 240.6367 | 100.0594 | 959.1269 | 919.9998 | 166.1673 |  | 1029.6801 | 317.0671 | 0.2002 | 1879.1267 | 1879.1267 | 1879.1267 | 0 | 1278.7301 | 600.3966 | 0.65565 | 0.053255 | 0.26061 | 0.011331 | 0.019153 | 1232.057 | 100.0733 | 489.713 | 21.2918 | 35.9916 | 1879.1267
4 | Falakata | 68.1981 |  |  | 714.6346 |  |  | 782.8327 |  | 436.3116 | 21.894 | 137.9676 | 4.7618 | 7.6519 | 608.5869 | 174.2458 | 102.3293 | 292.4339 | 316.153 | 44.8451 |  | 288.4795 | 75.9504 | 0.064838 | 604.1064 | 553.8766 | 608.5869 | 54.7103 | 423.0094 | 185.5775 | 0.71693 | 0.035975 | 0.2267 | 0.0078243 | 0.012573 | 436.3116 | 21.894 | 137.9676 | 4.7618 | 7.6519 | 608.5869
5 | Kalchini | 43.4726 |  |  | 883.7538 |  |  | 927.2264 |  | 524.7777 | 28.468 | 157.3777 | 30.0121 | 12.0113 | 752.6468 | 174.5796 | 100.7897 | 214.0691 | 538.5777 | 90.2812 | 4.3138 | 161.1674 | -1.7413 | 0.080185 | 752.6468 | 752.6468 | 752.6468 | 0 | 466.2353 | 286.4115 | 0.69724 | 0.037824 | 0.2091 | 0.039875 | 0.015959 | 524.7777 | 28.468 | 157.3777 | 30.0121 | 12.0113 | 752.6468
6 | Kumargram | 10.6689 |  |  | 1101.0302 |  |  | 1111.6991 |  | 677.772 | 46.4093 | 304.2335 | 12.4115 | 17.4522 | 1058.2784 | 53.4207 | 86.3088 | 530.3212 | 527.9572 | 81.51 |  | 425.8799 | 127.9529 | 0.11275 | 1050.4872 | 1046.5287 | 1058.2784 | 11.7497 | 748.4184 | 309.86 | 0.64045 | 0.043854 | 0.28748 | 0.011728 | 0.016491 | 677.772 | 46.4093 | 304.2335 | 12.4115 | 17.4522 | 1058.2784
7 | Madarihat-Birpara | 21.0557 |  |  | 932.505 |  |  | 953.5607 |  | 515.1237 | 22.1081 | 261.3273 | 12.3966 | 29.9121 | 840.8678 | 112.6929 | 84.7071 | 325.6474 | 515.2204 | 84.9085 |  | 297.8522 | 129.4026 | 0.089584 | 840.8678 | 840.8678 | 840.8678 | 0 | 550.8539 | 290.0139 | 0.61261 | 0.026292 | 0.31078 | 0.014743 | 0.035573 | 515.1237 | 22.1081 | 261.3273 | 12.3966 | 29.9121 | 840.8678
8 | Mal | 52.4402 |  |  | 846.3746 |  |  | 898.8148 |  | 546.4054 | 32.3412 | 151.0604 | 3.5171 | 8.0418 | 741.3659 | 157.449 | 98.1499 | 367.8294 | 373.5364 | 95.95 |  | 340.58 | 55.698 | 0.078984 | 741.3659 | 567.0824 | 741.3659 | 174.2835 | 567.0824 | 174.2835 | 0.73703 | 0.043624 | 0.20376 | 0.0047441 | 0.010847 | 546.4054 | 32.3412 | 151.0604 | 3.5171 | 8.0418 | 741.3658
9 | Matiali | 19.6377 |  |  | 362.7362 |  |  | 382.3739 |  | 267.746 | 11.3477 | 42.357 | 2.3641 | 4.8742 | 328.6891 | 53.6848 | 101.0225 | 147.3002 | 181.3889 | 83.8542 |  | 105.3133 | 30.4161 | 0.035018 | 328.6891 | 328.6891 | 328.6891 | 0 | 234.0252 | 94.6639 | 0.81459 | 0.034524 | 0.12887 | 0.0071925 | 0.014829 | 267.746 | 11.3477 | 42.357 | 2.3641 | 4.8742 | 328.6891
10 | Maynaguri | 90.7682 |  |  | 992.4715 |  |  | 1083.2396 |  | 720.9149 | 24.6948 | 116.9146 | 3.4251 | 8.6009 | 874.5503 | 208.6893 | 99.2579 | 266.2758 | 608.2746 | 80.1736 |  | 319.8161 | -30.1845 | 0.093173 | 868.1118 | 850.1292 | 874.5503 | 24.4211 | 620.145 | 254.4053 | 0.82433 | 0.028237 | 0.13369 | 0.0039164 | 0.0098347 | 720.9149 | 24.6948 | 116.9146 | 3.4251 | 8.6009 | 874.5503
11 | Nagrakata | 10.2604 |  |  | 313.2509 |  |  | 323.5113 |  | 160.7253 | 12.1104 | 78.0833 | 18.0807 | 2.4778 | 271.4775 | 52.0338 | 86.6238 | 73.3785 | 198.0991 | 29.6664 |  | 11.6217 | 42.3664 | 0.028923 | 271.4775 | 271.4775 | 271.4775 | 0 | 170.4715 | 101.006 | 0.59204 | 0.044609 | 0.28762 | 0.066601 | 0.009127 | 160.7253 | 12.1104 | 78.0833 | 18.0807 | 2.4778 | 271.4775
12 | Rajganj | 15.6417 |  |  | 508.1346 |  |  | 523.7763 |  | 281.7259 | 11.9049 | 45.9513 | 3.0753 | 16.6054 | 359.2629 | 164.5134 | 100.4489 | 158.2235 | 201.0394 | 52.4855 |  | 135.0877 | 4.9612 | 0.038275 | 359.2629 | 359.2629 | 359.2629 | 0 | 250.2098 | 109.0531 | 0.78418 | 0.033137 | 0.1279 | 0.0085601 | 0.046221 | 281.7259 | 11.9049 | 45.9513 | 3.0753 | 16.6054 | 359.2629
13 | Sadar | 36.488 |  |  | 651.7017 |  |  | 688.1898 |  | 300.32 | 19.4183 | 97.8686 | 6.5351 | 58.2542 | 482.3963 | 205.7934 | 97.411 | 198.2151 | 284.1812 | 61.025 |  | 59.2134 | 53.3488 | 0.051393 | 482.3963 | 482.3963 | 482.3963 | 0 | 303.7427 | 178.6536 | 0.62256 | 0.040254 | 0.20288 | 0.013547 | 0.12076 | 300.32 | 19.4183 | 97.8686 | 6.5351 | 58.2542 | 482.3963
| Total | 506.0906 | 0 | 0 | 10635.5048 |  | 0 | 11141.5953 | 0 | 6494.2447 | 356.2732 | 2137.5978 | 187.7107 | 210.5102 | 9386.3365 | 1755.2588 | 1256.5318 | 4111.6353 | 5274.7013 | 969.5746 |  | 3352.1394 | 874.1785 |  | 9363.2137 | 8976.7386 | 9386.3365 | 409.5979 | 9795.9344 | [11 empty] | 9386.3365
1 | Line Deptt. | 222.78 |  |  | 102.5618 |  |  | 325.3418 |  | 227.6569 |  |  |  |  | 227.6569 | 97.6849 |  | 83.25 | [6 empty] | 45.9803
2 | District Cell | 983.81 |  | 555.56 | 9000 | 1033.33 | 0 | 11572.7 |  |  |  |  | 30.151 | 22.857 | 53.008 |  |  | 29.3346 | [6 empty] | 558.1261 |  | 41.962 | 0.5688 | 23.868 | 23.868 | 18.094
| Total | 1206.59 | 0 | 555.56 | 9000 | 1033.33 | 0 | 11898.0418 |  | 227.6569 | 0 | 0 | 30.151 | 22.857 | 280.6649 |  |  | 333.6728
| G.T. | 1712.6806 | 0 | 555.56 | 9000 | 1033.33 | 0 | 12301.5706 | 0 | 6721.9017 | 356.2732 | 2137.5978 | 217.8616 | 233.3672 | 9667.0014 | 2634.5692 | 5238.4338 | 4445.3081 |  | 4428.5677 |  |  |  | 66.2123 | 9643.8786
[9 empty] | -680.5527 | -908.2096 |  |  | 1845.9986 | 11513 | 9317.2334 |  | -57.7746 | 43.0151 | [5 empty] | 7486.3369 | -45.9803
[10 empty] | 4864941 |  |  |  | 0.97097 | 9046.7234 | [8 empty] | 7767.0018 | 9257.4035 |  | 10467.0014
[10 empty] | 48.6494 |  |  | District Programme Coordinator |  | 8758.7918 | [9 empty] | 8976.7386 |  | 9257.4035
[10 empty] | 53.008 |  |  | MGNREGS, Jalpaiguri | [11 empty] | -409.5979
[9 empty] | 0.5688 | 0.4312 |  |  | & | [11 empty] | 10186.3365 | 10467.0014
[9 empty] | 27.6718 | 20.9776 |  |  | District Magistrate | [11 empty] | 8758.7918
[13 empty] | Jalpaiguri | [10 empty] | exp. 4 d month | 1708.2096
0.5688
53.008
30.151
[13 empty] | 30.151 | 22.857
Note on K27: N.R.E.G.S.4: Jan' 11
Note on N28: N.R.E.G.S.4: Jan' 11
Note on O28: N.R.E.G.S.4: Jan' 11

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2010-11 Up to the Month of January' 2011 | [19 empty] | Physical Performance Under NREGA During the year 2010-11 Up to the Month of January' 2011 | [17 empty] | Physical Performance Under NREGA During the year 2010-11 Up to the Month of January' 2011
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 506 | 820495.1791 | 375.4107 | 805 | 1307483.7826 | 582.2547 | 245 | 1018.5135 | 186.482 | 324 | 1413.8714 | 198.7426 | 329 | 417.7852 | 267.1007 | 282 | 282.6618 | 216.9278 | 341 | 817.5662 | 181.8673 | 193 | 403.6587 | 97.6974 | 123 | 86671.6889 | 98.6783 | 124 | 95496.4026 | 71.8267 | 1098 | 3328.4649 | 1198.4054 | 739 | 2632.8067 | 601.4416 | 433 | 363.2721 | 723.2407 | 444 | 279.8421 | 616.4042 | 1050 | 1810.1564 | 1546.5606 | 1168 | 578.0567 | 2252.7318 | 0 | 0 | 0 | 0 | 0 | 0 | 4125 | 4577.7457 | 4079 | 4638.0269 | 9215.7726 | 9215.7726 | 0
District Magistrate
Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2010-11 Up to the Month of January' 2011
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 2306 | 326 | 256.6169 | 1 | 219.6169 | 38 | 0 | 0 | 0 | 1 | 2632 | 257.6169 | 0.097508 | 258 | 257.6169 | 257.6169 | 219.6169 | 256.6169
2 | Alipurduar-II | 1988 | 384 | 109.6852 | 4 | 75.6852 | 38 | 0 | 0 | 0 | 0 | 2372 | 113.6852 | 0.04303 | 114 | 113.6852 | 113.6852 | 75.6852 | 109.6852
3 | Dhupguri | 7989 | 658 | 796.2263 | 10 | 764.2263 | 42 | 0 | 0 | 3 | 0 | 8647 | 806.2263 | 0.30516 | 806 | 806.2263 | 806.2263 | 764.2263 | 796.2263
4 | Falakata | 1657 | 1548 | 10.5588 | 3 | -20.4412 | 34 | 0 | 0 | 1 | 1 | 3205 | 13.5588 | 0.005132 | 14 | 13.5588 | 13.5588 | -20.4412 | 10.5588
5 | Kalchini | 3182 | 189 | 416.2794 | 3 | 387.2794 | 32 | 0 | 0 | 0 | 1 | 3371 | 419.2794 | 0.1587 | 419 | 419.2794 | 419.2794 | 387.2794 | 416.2794
6 | Kumargram | 7838 | 53 | 16.7307 | 1 | -29.2693 | 47 | 0 | 0 | 1 | 0 | 7891 | 17.7307 | 0.0067111 | 18 | 17.7307 | 17.7307 | -29.2693 | 16.7307
7 | Madarihat-Birpara | 3839 | 185 | 355.0442 | 10 | 335.0442 | 30 | 0 | 0 | 0 | 0 | 4024 | 365.0442 | 0.13817 | 365 | 365.0442 | 365.0442 | 335.0442 | 355.0442
8 | Mal | 3785 | 364 | 272.2617 | 1 | 239.2617 | 34 | 0 | 0 | 0 | 0 | 4149 | 273.2617 | 0.10343 | 273 | 273.2617 | 273.2617 | 239.2617 | 272.2617
9 | Matiali | 1035 | 910 | 251.402 | 1 | 174.402 | 78 | 0 | 0 | 1 | 1 | 1945 | 252.402 | 0.095534 | 252 | 252.402 | 252.402 | 174.402 | 251.402
10 | Maynaguri | 2537 | 2062 | 987.7484 | 1 | 946.7484 | 42 | 0 | 0 | 0 | 0 | 4599 | 988.7484 | 0.37424 | 989 | 988.7484 | 988.7484 | 946.7484 | 987.7484
11 | Nagrakata | 617 | 704 | 180.4791 | 1 | 150.4791 | 31 | 0 | 0 | 1 | 1 | 1321 | 181.4791 | 0.06869 | 181 | 181.4791 | 181.4791 | 150.4791 | 180.4791
12 | Rajganj | 1032 | 877 | 180.5221 | 2 | 128.5221 | 54 | 0 | 0 | 0 | 0 | 1909 | 182.5221 | 0.069085 | 183 | 182.5221 | 182.5221 | 128.5221 | 180.5221
13 | Sadar | 1244 | 452 | 250.445 | 3 | 215.445 | 38 | 0 | 0 | 1 | 0 | 1696 | 253.445 | 0.095929 | 253 | 253.445 | 253.445 | 215.445 | 250.445
| Total | 39049 | 8712 | 4084 | 41 | 3587 | 538 | 0 | 0 | 8 | 5 |  | 2642 |  |  | 4125
|  |  |  | 2642 |  | 2642 | [6 empty] | 2642
|  |  |  | -1442 |  | -945
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of January' 2011)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | - | - | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of January' 2011)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | - | - | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri