## Part-I
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of May' 2010
MPR- Part-I
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Register | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals | Avg. No. of Employment Provided per Household | % Women
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C | bar: 9
1 | 2 |  | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 39550 | 20568 | 8563 | 10418 | 39549 | 3781 |  | 3781 | 3525 |  | 0.42216 | 0.10733 | 0.14313 | 0.67262 | 0.24674 | 0.05173 | 0 | 225 | 3 | 17.7896 | 36.68% | 36.68% | 36.14% | 0.24674 | 0.05173 | 100
2 | Alipurduar-II | 41382 | 19699 | 9478 | 12205 | 41382 | 1920 |  | 1920 | 1920 |  | 0.79276 | 0.02415 | 0.36661 | 1.1835 | 0.64913 | 0.09435 | 0 | 0 | 0 | 61.6416 | 54.85% | 54.85% | 25.74% | 0.64913 | 0.09435 | 30.1477 |  | 5.2162 | 50.17% | 6.8404 | 9.4457 | 0.84276
3 | Dhupguri | 76095 | 38753 | 16411 | 20928 | 76092 | 9414 | 3563347 | 11500 | 7771 | 403965.9 | 1.7586 | 0.46903 | 0.87984 | 3.1074 | 0.95707 | 0.2037 | 0 | 690 | 15 | 27.0211 | 30.8% | 30.8% | 23.15% | 0.95707 | 0.2037 | 99.9678
4 | Falakata | 47514 | 21838 | 9512 | 16159 | 47509 | 8959 |  | 8664 | 7308 |  | 0.86135 | 0.25075 | 0.40455 | 1.5166 | 0.78598 | 0.07249 | 0 | 381 | 13 | 17.5052 | 51.82% | 51.82% | 17.92% | 0.78598 | 0.07249 | 53.0423
5 | Kalchini | 54803 | 8271 | 30850 | 15361 | 54482 | 1159 |  | 1101 | 1014 |  | 0.12573 | 0.27049 | 0.21939 | 0.61561 | 0.24461 | 0 | 0 | 816 | 6 | 55.9138 | 39.73% | 39.73% | 0% | 0.24461 | 0 | 122.8056 | 75.6005
6 | Kumargram | 38333 | 15435 | 13492 | 9346 | 38273 | 11280 |  | 11169 | 9872 |  | 0.71959 | 1.0794 | 0.59966 | 2.3986 | 0.8718 | 0.2044 | 0 | 4879 | 270 | 21.4759 | 36.35% | 36.35% | 34.09% | 0.8718 | 0.2044 | 81
7 | Madarihat-Birpara | 37686 | 7724 | 16212 | 13750 | 37686 | 2001 |  | 2001 | 2001 |  | 0.19276 | 0.29604 | 0.20253 | 0.69133 | 0.33653 | 0.07264 | 0 | 53 | 110 | 34.5492 | 48.68% | 48.68% | 35.87% | 0.33653 | 0.07264 | 100.0857
8 | Mal | 57043 | 18016 | 20467 | 18560 | 57043 | 13279 |  | 13279 | 11733 |  | 0.45236 | 0.08017 | 0.22562 | 0.75815 | 0.3353 | 0.09457 | 0 | 239 | 0 | 5.7094 | 44.23% | 44.23% | 41.92% | 0.3353 | 0.09457 | 103.4985
9 | Matiali | 24986 | 5886 | 12977 | 6057 | 24920 | 6696 |  | 6696 | 5770 |  | 0.18845 | 0.39932 | 0.11265 | 0.70042 | 0.35313 | 0.02645 | 0 | 56 | 0 | 10.4603 | 50.42% | 50.42% | 23.48% | 0.35313 | 0.02645 | 99.5651
10 | Maynaguri | 65705 | 49671 | 1040 | 14813 | 65524 | 3643 |  | 3643 | 3643 |  | 1.9963 | 0.02644 | 0.31314 | 2.3359 | 0.85086 | 0.04583 | 0 | 397 | 13 | 64.1202 | 36.43% | 36.43% | 14.64% | 0.85086 | 0.04583 | 50.3382
11 | Nagrakata | 25544 | 3975 | 14863 | 6664 | 25502 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! |  |  | 0 | 0 | #DIV/0!
12 | Rajganj | 49969 | 29448 | 2720 | 17645 | 49813 | 370 |  | 334 | 334 |  | 0.16478 | 0.08483 | 0.13615 | 0.38576 | 0.23254 | 0.09394 | 0 | 573 | 26 | 115.4969 | 60.28% | 60.28% | 68.99% | 0.23254 | 0.09394 | 103.2588 | 39.8331 | 83.2588 | 51.91% |  |  | 5.2162
13 | Sadar | 58703 | 37365 | 4051 | 17287 | 58703 | 892 |  | 162 | 162 |  | 0.15469 | 0.00516 | 0.05581 | 0.21566 | 0.07249 | 0.03738 | 0 | 65 | 0 | 133.1235 | 33.61% | 33.61% | 66.98% | 0.07249 | 0.03738 | 208.0907
| Total: | 617313 | 276649 | 160636 | 179193 | 616478 | 63394 | 3563347 | 64250 | 55053 | 403965.9 | 7.8295 | 3.0931 | 3.6591 | 14.5817 | 5.9362 | 0.99748 | 0 | 8374 | 456 | 22.6953 | 40.71% |  |  |  |  | 46.86 | 0.31118
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
Part-II
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2010-11 Up to the Month of May' 2010
Jalpaiguri District | [14 empty] | (Rs. in lakh)
Sl. No. | Name of the Block | Actual O.B. as on 01.04.08 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12) | Balance |  | Expenditure up to prev. months | expenditure during the month | Balance | Balance | Balance
[13 empty] | Recurring | Non-Recurring
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | 36.1802 |  |  | 147.362 |  |  | 183.5422 |  | 67.2624 | 3.6356 | 41.7353 | 4.8452 | 1.4935 | 118.9721 | 64.5701 | 100 | 61.8452 | 57.1269 | 61.85 |  | -293.9296 | -6.3186
2 | Alipurduar-II | 39.3776 |  |  | 189.1001 |  |  | 228.4777 |  | 35.6804 | 0.85406 | 10.3425 | 2.5715 | 0.0565 | 49.5049 | 178.9728 | 30.1477 | 12.6472 | 36.8577 | 36.8577 |  | -549.233 | -127.4062
3 | Dhupguri | 52.1498 |  |  | 406.561 |  |  | 458.7108 |  | 310.643 | 14.7782 | 90.6642 | 9.8803 | 2.3453 | 428.3109 | 30.3999 | 99.9678 | 262.1436 | 166.1673 | 166.1673 |  | -421.1357 | -81.9817
4 | Falakata | 61.0982 |  |  | 182.9717 |  |  | 244.0699 |  | 80.4467 | 5.0998 | 39.8221 | 1.2034 | 1.9711 | 128.5432 | 115.5267 | 53.0423 | 83.6981 | 44.8451 | 44.8451 |  | -191.5642 | -22.1951
5 | Kalchini | 59.3163 |  |  | 122.3488 |  |  | 181.6652 |  | 75.6005 | 3.1667 | 19.5008 | 4.639 | 1.1815 | 104.0885 | 77.5767 | 122.8056 | 13.8073 | 90.2812 | 90.2812 | 4.3138 | -487.391 | -139.6182
6 | Kumargram | 31.0914 |  |  | 254.755 |  |  | 285.8464 |  | 194.2903 | 12.2646 | 65.622 | 2.8133 | 4.0588 | 279.049 | 6.7973 | 81 | 126.8291 | 152.2199 | 81.51 |  | -353.3495 | -110.6586
7 | Madarihat-Birpara | 35.3853 |  |  | 162.1865 |  |  | 197.5718 |  | 69.1923 | 3.1289 | 43.3822 | 1.4974 | 6.3605 | 123.5613 | 74.0105 | 100.0857 | 38.6527 | 84.9085 | 84.9085 |  | -419.4543 | -88.5425
8 | Mal | 61.0063 |  |  | 186.1169 |  |  | 247.1232 |  | 78.4674 | 5.6098 | 9.9599 | 1.2752 | 0.64166 | 95.9539 | 151.1693 | 103.4985 | 95.9539 | 0 | 95.95 |  | -304.832 | -85.4025
9 | Matiali | 31.297 |  |  | 102.7277 |  |  | 134.0246 |  | 69.7374 | 2.4988 | 12.5906 | 0.71539 | 0.84239 | 86.3845 | 47.6401 | 99.5651 | 2.5303 | 83.8542 | 83.8542 |  | -136.9913 | 0.64965
10 | Maynaguri | 109.5885 |  |  | 209.617 |  |  | 319.2055 |  | 117.585 | 5.0644 | 21.3099 | 0.70539 | 1.9251 | 146.5897 | 172.6158 | 50.3382 | 66.4161 | 80.1736 | 80.1736 |  | -408.1445 | -125.7892
11 | Nagrakata | 10.2962 |  |  | 78.234 |  |  | 88.5302 |  | 29.2919 | 1.5978 | 9.1104 | 1.7618 | 0.40753 | 42.1695 | 46.3607 | #DIV/0! | 12.5031 | 29.6664 | 29.6664 |  | -217.6864 | -26.6065
12 | Rajganj | -27.269 |  |  | 138.5536 |  |  | 111.2846 |  | 39.8331 | 1.3495 | 12.4096 | 0.56325 | 0.92622 | 55.0817 | 56.2029 | 103.2588 | 2.5962 | 52.4855 | 52.4855 |  | -169.0935 | -28.5805
13 | Sadar | 11.9617 |  |  | 123.6825 |  |  | 135.6442 |  | 44.8768 | 3.6472 | 26.2127 | 0.76905 | 9.5731 | 85.0788 | 50.5653 | 208.0907 | 24.0538 | 61.025 | 61.025 |  | -338.1041 | -18.3071
| Total | 511.4795 | 0 | 0 | 2304.2167 |  | 0 | 2815.6962 | 0 | 1212.9072 | 62.6953 | 402.6622 | 33.2402 | 31.7833 | 1743.2882 | 1072.4081 | #DIV/0! | 803.6767 | 939.6115 | 969.5746 |  | -4290.9089 | -860.7571
1 | Line Deptt. | 292.6704 |  |  | 50.75 |  |  | 343.4204 |  | 0 |  |  |  |  | 0 | 343.4204
2 | District Cell | 989.9174 |  | 555.56 | 200 | 0 | 0 | 1745.4774 |  |  |  |  | 0.34502 | 0.275 | 0.62002
| Total | 1282.5878 | 0 | 555.56 | 200 | 0 | 0 | 2088.8978 |  | 0 | 0 | 0 | 0.34502 | 0.275 | 0.62002
| G.T. | 1794.0673 | 0 | 555.56 | 200 | 0 | 0 | 2549.6273 | 0 | 1212.9072 | 62.6953 | 402.6622 | 33.5852 | 32.0583 | 1743.9082 | 805.7192 | 5238.4338 |  |  | -3494.5256
[17 empty] | 100.6626 | 223.4682
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
Note on N28: NREGS-4: APR-10
Note on O28: NREGS-4: APR-10

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
National Rural Employment Guarantee Act (NREGA) | [19 empty] | National Rural Employment Guarantee Act (NREGA) | [17 empty] | National Rural Employment Guarantee Act (NREGA)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2010-11 Up to the Month of May' 2010 | [19 empty] | Physical Performance Under NREGA During the year 2010-11 Up to the Month of May' 2010 | [17 empty] | Physical Performance Under NREGA During the year 2010-11 Up to the Month of May' 2010
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 105 | 172999.925 | 79.75 | 315 | 516077.5247 | 138.3887 | 13 | 59.56 | 9.14 | 114 | 497.58 | 69.87 | 58 | 76.39 | 49.0774 | 81 | 95.69 | 15.6955 | 9 | 18.69 | 4.2405 | 95 | 113.69 | 8.59 | 39 | 27938.82 | 33.59 | 62 | 46569.79 | 17.4759 | 146 | 469.39 | 168.97 | 408 | 1401.9922 | 25.58 | 101 | 79.6282 | 104.5282 | 235 | 186.98 | 186.1227 | 305 | 484.3982 | 341.2794 | 698 | 338.7478 | 425.9665 | 0 | 0 | 0 | 0 | 0 | 0 | 776 | 790.5755 | 2008 | 887.6892 | 1678.2647 | 1678.2647 | 0
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-IV
Part-IV
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2010-11 Up to the Month of May' 2010
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 686 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 1 | 686 | 686 | 686 | 784 | 784 | 144
2 | Alipurduar-II | 1208 | 0 | 27 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 1208 | 1208 | 1208 | 846 | 846 | 172
3 | Dhupguri | 3171 | 0 | 196 | 0 | 196 | 0 | 0 | 0 | 1 | 0 | 3171 | 3171 | 3171 | 1431 | 1431 | 143
4 | Falakata | 1548 | 0 | 52 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 1548 | 1548 | 1548 | 900 | 900 | 138
5 | Kalchini | 628 | 0 | 153 | 0 | 153 | 0 | 0 | 0 | 0 | 1 | 628 | 628 | 628 | 841 | 841 | 95
6 | Kumargram | 2448 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 2448 | 2448 | 2448 | 572 | 572 | 158
7 | Madarihat-Birpara | 705 | 0 | 51 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 705 | 705 | 705 | 881 | 881 | 231
8 | Mal | 774 | 0 | 42 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 774 | 774 | 774 | 677 | 677 | 102
9 | Matiali | 715 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 2 | 0 | 715 | 715 | 715 | 356 | 356 | 75
10 | Maynaguri | 2384 | 0 | 122 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 2384 | 2384 | 2384 | 2492 | 2492 | 121
11 | Nagrakata | 0 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 342 | 68
12 | Rajganj | 394 | 0 | 33 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 394 | 394 | 394 | 659 | 659 | 91
13 | Sadar | 220 | 0 | 18 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 1086 | 1086 | 143
| Total | 14881 | 0 | 776 | 0 | 776 | 0 | 0 | 0 | 3 | 2
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
National Rural Employment Guarantee Act (NREGA)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of May' 2010)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | - | - | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
National Rural Employment Guarantee Act (NREGA)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of May' 2010)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | - | - | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri