## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of APRIL 2012 (for the financial year 2012-13)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 |  | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 40448 | 21046 | 8586 | 10816 | 40448 | 1080 | 3518 | 1080 | 1080 | 36109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Alipurduar-II | 45215 | 17364 | 5073 | 22778 | 45215 | 1662 | 4080 | 1662 | 1662 | 41903 | 0.11714 | 0.05026 | 0.10662 | 0.27402 | 0.0976 | 0.06312 | 0 | 0 | 0
3 | Dhupguri | 80508 | 39105 | 16764 | 22691 | 78560 | 1827 | 9113 | 1827 | 1827 | 79022 | 0.10582 | 0.0078 | 0.07363 | 0.18725 | 0.06421 | 0.00442 | 0 | 66 | 5 |  | 0
4 | Falakata | 52321 | 23674 | 10067 | 18580 | 52321 | 0 | 7738 | 0 | 0 | 79488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Kalchini | 60769 | 8750 | 31469 | 19552 | 59771 | 1935 | 6923 | 1935 | 1935 | 71160 | 0.08667 | 0.19537 | 0.17373 | 0.45577 | 0.2243 | 0.0117 | 0 | 0 | 0 |  | 0
6 | Kumargram | 40417 | 16599 | 13635 | 10163 | 40397 | 2135 | 11414 | 264 | 264 | 228263 | 0.00087 | 0.0027 | 0.00176 | 0.00533 | 0 | 0 | 0 | 0 | 0
7 | Madarihat | 39294 | 7539 | 16324 | 15431 | 39294 | 0 | 7576 | 0 | 0 | 77856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Mal | 58540 | 18394 | 20606 | 19540 | 58540 | 1394 | 5804 | 1372 | 1372 | 59647 | 0.0377 | 0.04561 | 0.04084 | 0.12415 | 0.04469 | 0 | 0 | 0 | 0 |  | 0
9 | Matiali | 24986 | 5981 | 12141 | 6675 | 24797 | 0 | 2750 | 0 | 0 | 28234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Maynaguri | 70443 | 50663 | 1053 | 18261 | 69977 | 0 | 6639 | 0 | 0 | 41623 | 0.035 | 0 | 0.00603 | 0.04103 | 0.00903 | 0.00268 | 0 | 0 | 0
11 | Nagrakata | 26331 | 3949 | 15086 | 7296 | 26331 | 0 | 3011 | 0 | 0 | 30927 | 0.13486 | 0.15361 | 0.17553 | 0.464 | 0.12488 | 0.07039 | 0 | 110 | 0 |  | 0
12 | Rajganj | 51625 | 29922 | 2727 | 18976 | 51625 | 0 | 3622 | 0 | 0 | 37189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Sadar | 58642 | 34782 | 4355 | 19505 | 58642 | 0 | 3619 | 0 | 0 | 37139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54
| Total: | 649539 | 277768 | 157886 | 210264 | 645918 | 10033 | 75807 | 8140 | 8140 | 848560 | 0.51806 | 0.45535 | 0.57814 | 1.5515 | 0.56471 | 0.15231 | 0 | 176 | 59 |  | 0
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
Employment provided to HHS: 8140 nos.
Persondays[in lac]: Total: 1.55, SCs: 0.51 [33.38%], STs: 0.45 [29.35% ], Women : 0.56 [36.39%], Others: 0.57 [37.26%]
Works taken up: 3493 nos.,Works completed:139 nos., Works in progress: 3354 nos.
Total exp:351.88 lac, GP wise avg exp:2.39 lac

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2012-13 Up to the Month of APRIL' 2012
[16 empty] | -368.793 | 0 | -266.2758 | 264.1093 | -80.1736 | 0 | 552.5678
Sl. No. | Name of the Block | Actual O.B. as on 01.04.12 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh)
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12) | Balance |  | Expenditure up to prev. months | expenditure during the month | Balance | Balance | Balance
[13 empty] | Recurring | Non-Recurring
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | -24.5211 |  |  | 131.95 |  |  | 107.4289 | 72.195 | 0 | 0.052 | 0.0583 | 0.0605 | 0.0891 | 0.2599 | 107.169 | #REF! | 274.4036 | -274.1437 | 61.85 |  | -412.6418
2 | Alipurduar-II | 44.2983 |  |  | 200.975 |  |  | 245.2733 | 129.475 | 107.3209 | 4.8669 | 31.2234 | 1.3899 | 0.6947 | 145.4957 | 99.7776 | #REF! | 304.4107 | -158.915 | 36.8577 |  | -453.2422
3 | Dhupguri | 106.7473 |  |  | 190.82 |  |  | 297.5673 | 221.8524 | 27.2989 | 0.96525 | 1.5 | 0.164 | 0.1629 | 30.091 | 267.4763 | #REF! | 959.1269 | -929.0359 | 166.1673 |  | -819.3556
4 | Falakata | 42.231 |  |  | 375.55 |  |  | 417.781 | 158.9875 | 0 | 0.0741 | 0.2794 | 1.9224 | 0.05282 | 2.3287 | 415.4523 | #REF! | 292.4339 | -290.1052 | 44.8451 |  | -317.7787
5 | Kalchini | 53.1356 |  |  | 157.325 |  |  | 210.4606 | 142.325 | 45.6872 | 5.021 | 20.1033 | 2.8979 | 0.3371 | 74.0464 | 136.4142 | #REF! | 214.0691 | -140.0227 | 90.2812 | 4.3138 | -517.4331
6 | Kumargram | 39.365 |  |  | 263.9 |  |  | 303.265 | 234.5125 | 8.9271 | 1.0881 | 7.3612 | 0.4012 | 0.35466 | 18.1322 | 285.1327 | #REF! | 530.3212 | -512.189 | 81.51 |  | -614.2663
7 | Madarihat | 8.2693 |  |  | 82.215 |  |  | 90.4843 | 155.7 | 0 | 0.11424 | 0.08 | 0 | 0.1484 | 0.34264 | 90.1416 | #DIV/0! | 325.6474 | -325.3047 | 84.9085 |  | -542.6729
8 | Mal | 92.7703 |  |  | 30.45 |  |  | 123.2203 | 119.2875 | 12.9324 | 0.10725 | 0.85742 | 2.1156 | 0.27836 | 16.291 | 106.9293 | 104.1675 | 367.8294 | -351.5384 | 95.95 |  | -384.4949
9 | Matiali | 18.3071 |  |  | 84.245 |  |  | 102.5521 | 56.4625 | 0 | 1.597 | 0.1 | 0.2412 | 0.46186 | 2.4001 | 100.1519 | #REF! | 147.3002 | -144.9 | 83.8542 |  | -220.9757
10 | Maynaguri | 152.7345 |  |  | 218.225 |  |  | 370.9595 | 199.2663 | 0 | 0 | 1.7495 | 0.26497 | 0.15199 | 2.1665 | 368.793 | 0 | 266.2758 | -264.1093 | 80.1736 |  | -552.5678
11 | Nagrakata | 23.4309 |  |  | 85.26 |  |  | 108.6909 | 61.8375 | 16.6036 | 1.0125 | 4.8622 | 0.39898 | 0.07541 | 22.9526 | 85.7383 | #REF! | 73.3785 | -50.4259 | 29.6664 |  | -236.9033
12 | Rajganj | -4.6747 |  |  | 138.04 |  |  | 133.3653 | 74.35 | 0 | 0.33345 | 2.7391 | 0.08816 | 0.17063 | 3.3314 | 130.0339 | #REF! | 158.2235 | -154.8921 | 52.4855 |  | -220.8439
13 | Sadar | 76.5827 |  |  | 204.015 |  |  | 280.5977 | 74.2875 | 26.1709 | 1.3793 | 0.13765 | 3.0913 | 0.37589 | 31.155 | 249.4426 | #REF! | 198.2151 | -167.0601 | 61.025 |  | -392.0279
| Total | 628.6761 | 0 | 0 | 2162.97 |  | 0 | 2791.6461 | 1700.5387 | 244.9409 | 16.611 | 71.0515 | 13.0361 | 3.3538 | 348.9933 | 2442.6528 | #REF! | 4111.6353 | -3762.642 | 969.5746 |  | -5685.2038
1 | Line Deptt. | 216.61 |  |  | 6.4873 |  |  | 223.0973 |  | 0 | 0 | 0 | 0 | 0 | 0 | 223.0973 |  | 83.25
2 | District Cell | 670.3172 |  |  | 2500 | 0 |  | 3170.3172 |  |  |  |  | 2.77 | 0.12 | 2.89 |  |  | 29.3346
| Total | 886.9272 | 0 | 0 | 2500 | 0 | 0 | 3393.4145 |  | 0 | 0 | 0 | 2.77 | 0.12 | 2.89 |  |  | 5.78
| G.T. | 1515.6033 | 0 | 0 | 2500 | 0 | 0 | 4015.6033 | 1700.5387 | 244.9409 | 16.611 | 71.0515 | 15.8061 | 3.4738 | 351.8833 | 3663.72 | 5238.4338 | 4117.4153 |  | -4886.5505
DPC
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
Note on K25: MARCH' 2012
Note on N26: APRIL' 12
Note on O26: APRIL' 12

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2012-13 Up to the Month of APRIL' 2012 | [19 empty] | Physical Performance Under NREGA During the year 2012-13 Up to the Month of APRIL' 2012 | [17 empty] | Physical Performance Under NREGA During the year 2012-13 Up to the Month of APRIL' 2012
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 32 | 17661.3271 | 21.6064 | 728 | 30903.0577 | 35.0158 | 8 | 0.123 | 0 | 162 | 3.6226 | 2.9779 | 3 | 7.3177e-06 | 0.5044 | 159 | 35.0482 | 16.1757 | 0 | 0 | 0 | 10 | 0 | 0.75445 | 4 | 0.0023894 | 0.48931 | 333 | 3.2656 | 11.1583 | 28 | 5.7427 | 39.3935 | 629 | 119.0644 | 24.1826 | 14 | 2.85 | 25.788 | 373 | 36.9786 | 32.8993 | 50 | 25.5573 | 57.3513 | 927 | 207.1073 | 60.5463 | 0 | 0 | 0 | 33 | 139.68 | 3.7602 | 139 | 145.13 | 3354 | 187.47 | 332.6 | 332.6034 | -0.00336
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2012-13 Up to the Month of APRIL 2012
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 0 | 0 | 11 | 3 | 0 | 0 | 0 | 10 | 0 | 0
2 | Alipurduar-II | 292 | 0 | 11 | 0 | 284 | 0 | 1 | 0 | 8 | 0
3 | Dhupguri | 68.7802 | 275.1207 | 16 | 0 | 0 | 0 | 0 | 1 | 12 | 12
4 | Falakata | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Kalchini | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 16 | 0 | 0
6 | Kumargram | 2084 | 1 | 11 | 0 | 48 | 1 | 1 | 10 | 0 | 0
7 | Madarihat-Birpara | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0
8 | Mal | 0 |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Matiali | 0 | 49 | 5 | 0 | 0 | 6 | 0 | 5 | 0 | 0
10 | Maynaguri | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 2 | 0
11 | Nagrakata | 152 | 0 | 5 | 0 | 126 | 0 | 5 | 0 | 1 | 3
12 | Rajganj |  |  | 12 | 0
13 | Sadar |  |  | 14 | 0
| Total | 2596.7802 | 325.1207 | 146 | 3 | 458 | 7 | 7 | 52 | 23 | 15
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of APRIL' 2012)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of APRIL' 2012)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
APRIL 2011
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Alipurduar-I | 3802 | 0 | 0 | 35944 | 320 | 0 | 0 | 0 | 0
2 | Alipurduar-II | 7895 | 36 | 27.9404 | 26404 | 45 | 79.3804 | 107.3209 | 107.3209 | 0
3 | Dhupguri | 920 | 752 | 4.26 | 8751 | 3637 | 23.04 | 27.3 | 27.2989 | 0.00115
4 | Falakata | 15635 | 612 | 0 | 45236 | 59 | 0 | 0 | 0 | 0
5 | Kalchini | 18953 | 345 | 13.9022 | 34990 | 3086 | 31.785 | 45.6872 | 45.6872 | 0
6 | Kumargram | 4445 | 1606 | 2.9042 | 30311 | 5853 | 6.0229 | 8.9271 | 8.9271 | 0
7 | Madarihat | 4466 | 53 | 0 | 35893 | 4300 | 0 | 0 | 0 | 0
8 | Mal | 2380 | 11 | 0 | 32582 | 1389 | 12.9324 | 12.9324 | 12.9324 | 0
9 | Matiali | 0 | 0 |  | 51609 | 486 | 0 | 0 | 0 | 0
10 | Maynaguri | 7679 | 0 | 0 | 48857 | 0 | 0 | 0 | 0 | 0
11 | Nagrakata | 3213 | 0 | 3.4216 | 28403 | 0 | 13.182 | 16.6036 | 16.6036 | 0
12 | Rajganj | 2906 | 0 | 0 | 45847 | 4733 | 0 | 0 | 0 | 0
13 | Sadar | 2741 | 0 |  | 38657 | 0 | 26.17 | 26.17 | 26.1709 | -0.00086
Total |  | 75035 | 3415 | 52.4284 | 463484 | 23908 | 192.5127 | 244.9412 | 244.9409 | 0.00029