## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
Part - I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of March 2015 (for the financial year 2014-15)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals |  |  | 1.85
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Dhupguri | 81308 | 39729 | 16111 | 23803 | 79643 | 49736 | 78142 | 45140 | 745 | 2502708 | 2.0518 | 1.1863 | 2.6034 | 5.8416 | 1.989 | 0 | 0 | 18 | 13 | 34.0492 | 12.941
2 | Mal | 59222 | 18574 | 21679 | 18969 | 59222 | 26073 | 25823 | 26073 | 0 | 772288 | 1.1258 | 1.972 | 2.562 | 5.6598 | 2.3452 | 0 | 31 | 170 | 0 | 41.4363 | 21.7075
3 | Matiali | 26002 | 4908 | 10878 | 10216 | 26002 | 16789 | 8687 | 16789 | 139 | 256063 | 0.43607 | 1.0397 | 1.7196 | 3.1953 | 1.6692 | 0 | 19 | 88 | 18 | 52.2389 | 19.0322
4 | Maynaguri | 72002 | 41680 | 758 | 29675 | 72096 | 25994 | 15044 | 24217 | 3018 | 753217 | 2.9818 | 0.10543 | 2.0882 | 5.1754 | 1.9058 | 0.016652 | 53 | 12 | 0 | 36.8245 | 21.3711
5 | Nagrakata | 27399 | 4201 | 15542 | 7600 | 27343 | 14083 | 14010 | 14066 | 673 | 400280 | 0.82648 | 1.1793 | 0.74011 | 2.7459 | 1.2866 | 0.25658 | 10 | 92 | 17 | 46.8562 | 19.5215
6 | Rajganj | 51904 | 28046 | 2207 | 21573 | 51694 | 13967 | 12921 | 13967 | 925 | 412067 | 1.1001 | 0.05091 | 1.7119 | 2.8629 | 1.3817 | 0.66797 | 9 | 24 | 1 | 48.2636 | 20.4976
7 | Sadar | 62056 | 33976 | 4063 | 24017 | 62056 | 16746 | 16820 | 15838 | 2983 | 459088 | 1.6836 | 0.15506 | 1.3053 | 3.144 | 1.1578 | 0.04866 | 28 | 63 | 11 | 36.8263 | 19.8512
| Total: | 379893 | 171114 | 71238 | 135853 | 378056 | 163388 | 171447 | 156090 | 8483 | 5555711 | 10.2057 | 5.6887 | 12.7306 | 28.6249 | 11.7354 | 0.98986 | 150 | 467 | 60 | 40.9972 | 18.3387
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2014-15 Up to the Month of March ' 2015
1649.6699
Sl. No. | Name of the Block | Actual O.B. as on 01.04.14 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Authorisation of EFMS | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh) | [6 empty] | #REF!
|  |  | Central | State | Central | State |  |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[14 empty] | Recurring | Non-Recurring |  |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | [8 empty] | WAGE% | PER LABOUR
1 | Dhupguri | 29.1483 |  |  | 2899.8015 |  | 8.3822 | 548.69 | 3486.022 | 6229.099 | 2587.7315 | 177.0851 | 330.6557 | 21.7436 | 7.1646 | 3124.3806 |  | 28.4371 | #REF! | #REF! | 946.3318 | 16 | 195.2738 | 284.0346 | 82.8238 | 442.9849 | Dhupguri | 831.2044
2 | Mal | 12.7201 |  |  | 1240.7027 |  | 0.2718 | 430.72 | 1684.4146 | 1965.544 | 1272.1544 | 114.6914 | 200.9916 | 38.9577 | 22.8747 | 1649.6699 |  | 15.0147 | #REF! | #REF! | 394.9049 | 12 | 137.4725 | 149.97 | 77.1157 | 224.7706 | Malbazar | 402.7251
3 | Matiali | 15.5383 |  |  | 718.3597 |  | 0.50083 | 161.29 | 895.6888 | 656.885 | 756.26 | 68.7673 | 120.4965 | 11.0115 | 6.8807 | 963.416 |  | 8.7687 | #REF! | #REF! | 329.2062 | 5 | 192.6832 | 87.5833 | 78.4978 | #REF! | Matiali | 230.7365
4 | Maynaguri | 39.4891 |  |  | 1156.5605 |  | 1.2281 | 572.36 | 1769.6377 | 1970.207 | 1389.5902 | 95.5192 | 144.1166 | 94.1764 | 10.2002 | 1733.6026 |  | 15.7787 | 236.9127 | 1626.5029 | 421.4004 | 16 | 108.3502 | 157.6002 | 80.1562 | 268.497 | Maynaguri | 677.9344
5 | Nagrakata | 6.0022 |  |  | 804.1413 |  | 1.3888 | 242.31 | 1053.8423 | 1002.547 | 601.3209 | 69.5503 | 204.9686 | 20.9335 | 16.424 | 913.1974 |  | 8.3116 | 72.882 | 674.2029 | 284.0694 | 5 | 182.6395 | 83.0179 | 65.8479 | #REF! | Nagrakata | 243.0925
6 | Rajganj | 13.8428 |  |  | 731.3527 |  | 4.5871 | 283.75 | 1033.5326 | 1108.682 | 793.9619 | 58.7652 | 167.1906 | 31.1016 | 11.5387 | 1062.5581 | 51.1913 | 9.671 | 152.5963 | 946.5582 | 217.4445 | 12 | 88.5465 | 96.5962 | 74.7217 | 277.3279 | Rajganj | 282.2
7 | Sadar | 36.2088 |  |  | 1180.869 |  | 19.9529 | 378.54 | 1615.5707 | 1403.31 | 1290.1625 | 86.1383 | 140.2979 | 49.438 | 46.1921 | 1612.2289 |  | 14.674 | 121.9644 | 1412.1269 | 551.7063 | 14 | 115.1592 | 146.5663 | 80.0235 | 410.3531 | Sadar | 641.197
| Total | 152.9495 | 0 | 0 | 8731.7875 | 0 | 36.3117 | 2617.66 | 11538.7086 | 14336.274 | 8691.1815 | 670.517 | 1308.7176 | 267.3623 | 121.2751 | 11059.0535 |  | 20.9519 |  |  |  | 80 | 138.2382 | 1005.3685 | 78.5888
1 | Line Deptt. | 28.3699 |  |  | 147.49 |  |  |  | 175.8599 | 0 | 108.3691 | 10.5072 | 35.0382 | 0.99335 | 0 | 154.9079 |  | 10670.4161 |  |  |  | 10824.3307 |  | 75.7469
2 | District Cell | 1072.1861 |  |  | 13150 | 1625 | 45.92 |  | 15893.1061 |  |  |  |  | 41.5 | 8.04 | 49.54
| Total |  |  |  | 13150 |  |  |  | 16068.9659 |  | 108.3691 | 10.5072 | 35.0382 | 42.4933 | 8.04 | 204.4479
G.T. |  | 1253.5054 | 0 | 0 | 13150 | 1625 | 82.2317 | 2617.66 | 18728.3971 | 14336.274 | 8799.5507 | 681.0242 | 1343.7558 | 309.8556 | 129.3151 | 11263.5014
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2014-15 Up to the Month of March 2015 | [19 empty] | Physical Performance Under NREGA During the year 2014-15 Up to the Month of March 2015 | [17 empty] | Physical Performance Under NREGA During the year 2014-15 Up to the Month of March 2015
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 101 | 263030.8425 | 475.3449 | 147 | 25652.2106 | 118.1822 | 218 | 10905.0393 | 216.5397 | 298 | 11.35 | 88.6894 | 311 | 317.75 | 850.1498 | 325 | 31.1 | 474.2203 | 314 | 359.7839 | 461.384 | 475 | 35.7586 | 146.2817 | 96 | 159247.2726 | 137.1646 | 85 | 31872.0828 | 99.5089 | 534 | 527.8078 | 981.5283 | 350 | 232.7 | 409.6128 | 236 | 1522.8215 | 899.8716 | 240 | 63.0376 | 516.2799 | 829 | 1601.8885 | 2449.879 | 501 | 991.2 | 1594.6325 | 93 | 911.45 | 439.889 | 155 | 48 | 465.1721 | 2732 | 6911.751 | 2576 | 3912.58 | 10824.331 | 10824.3307
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2014-15 Up to the Month of March 2015
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Dhupguri | 6519.8577 | 26079.431 | 4 | 28 | 0 | 0.1 | 0 | 1 | 12 | 12
2 | Mal | 0 | 108 | 0 | 24 | 0 | 29 | 0 | 0 | 0 | 0
3 | Matiali | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 4
4 | Maynaguri | 3452 | 1900 | 6 | 26 | 0 | 18 | 0 | 16 | 1 | 1
5 | Nagrakata | 1846 | 1400 | 2 | 8 | 141 | 84 | 0 | 5 | 0 | 0
6 | Rajganj | 13940 | 1247 | 4 | 20 | 1266 | 65 | 0 | 12 | 0 | 0
7 | Sadar | 5303 | 659 | 0 | 28 | 341 | 62 | 0 | 14 | 0 | 0
| Total | 31060.8577 | 31393.431 | 16 | 144 | 1748 | 258.1 | 0 | 48 | 13 | 17
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of March 2015)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 126 | 102 | 5 | 3 | 14 | 12 | 7 | 7 | 7 | 6 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
FALSE

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of March 2015)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 2 | 100 | 0 | 3 | 0 | 13 | 0 | 7 | 0 | 6 | 5 | 5 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 91 | 940 | 17 | 3477
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
March 2015
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
3 | Dhupguri | 48629 | 0 | 1493.01 | 45291 | 250 | 1094.72 | 2587.73 | 2587.7315 | -0.00154 | 262.21 | 1755.22 | 1356.93 | 1148.62 | 1103.3396
8 | Mal | 11379 | 8 | 283.982 | 32627 | 1377 | 988.1724 | 1272.1544 | 1272.1544 | 0
9 | Matiali | 2753 | 80 | 83.52 | 24624 | 1459 | 672.74 | 756.26 | 756.26 | 0 |  | 341.33 | 1094.72 | 1436.05
10 | Maynaguri | 30456 | 0 | 698.2691 | 30156 | 0 | 691.3211 | 1389.5902 | 1389.5902 | 0
11 | Nagrakata | 3831 | 0 | 186.6616 | 29038 | 0 | 414.6593 | 601.3209 | 601.3209 | 0
12 | Rajganj | 4331 | 0 | 101.9811 | 51097 | 0 | 691.9808 | 793.9619 | 793.9619 | 0
13 | Sadar | 17039 | 225 | 412.8728 | 53037 | 597 | 877.2897 | 1290.1625 | 1290.1625 | 0
| Line dep. | 1000 |  | 50.185 | 2000 | 0 | 58.185 | 108.37 | 108.3691 | 0.00085
Total |  | 119418 | 313 | 3310.4816 | 267870 | 3683 | 5489.0684 | 8799.55 | 8799.5507 | -0.00069
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri