## 2016-17
sl | ID | Date | Block/District | First Name | Last Name | Address | GP | PO Complaint | PO Action | Final Action | Disposed or Not
1 | DPC0011 | 2016-01-11 | District | Sumit Sikder | & Others | Sakoajhora | Sakoajhora I | Irregularity in Tender process | Forwarded to the PO & BDO, Dhupguri vide Memo No. 1236/IV/2/MGNREGS dated 04-02-2016 of the ADPC & ADM(D), Jalpaiguri | NIT cancelled by the Pradhan
2 | DPC0012 | 2016-02-02 | District | Vishal Kujur | & Others | Gendrapara TG, Banarhat, Dhupguri | Banarhat I | Irregularity in MGNREGA | Forwarded to the PO & BDO, Dhupguri vide Memo No. 1252/IV/2/MGNREGS dated 09-02-2016 of the ADPC & ADM(D), Jalpaiguri | Pending
3 | DPC0013 | 2016-02-02 | District | Dipak | Roy | Chairman, Terai Udyog Engineers Co-operative Contract & Construction Society Ltd | Madhabdanga II | Non-payment of bill against material supply | Copy forwarded to the PO & BDO, Maynaguri vide Memo No. 1251/IV/2/MGNREGS dated 09-02-2016 of the ADPC & ADM(D), Jalpaiguri | Prodhan, Madhabdanga II vide Memo No. 399/Mad-II/2017 dated 09-03-2017 has assured to clear the outstanding amount at the earliest possible.
4 | DPC0014 | 2016-02-22 | District | Bidur Chhetri | & Others | Chamurchi, Dhupguri | Chamurchi | Issuance of Tender forms | Forwarded to the PO & BDO, Dhupguri vide Memo No. 1302/IV/2/MGNREGS datyed 23-02-2016 of the ADPC & ADM(D), Jalpaiguri | Pending
5 | DPC0015 | 2016-03-02 | District | Rabi Sarkar | & Others | Salbari, Dhupguri | Salbari I | Work order issued without Tender process | Forwarded to the PO & BDO, Dhupguri vide Memo No. 1343/IV/2/MGNREGS dated 02-03-2016 of the ADPC & ADM(G), Jalpaiguri | Anomalies detected. All the works were made stop vide Memo No. 1742/MGNREGS dated 04-03-2016 of the PO & BDO, Dhupguri
6 | DPC0016 | 2016-06-30 | District | Sanjay Oraon | & Others | Kathalguri Beech Line, Banarhat TG | Chamurchi | Irregularity in MGNREGA works | Forwarded to PO & BDO, Dhupguri vide Memo No. 1479/IV/2/MGNREGS dated 08-07-2016 of the DNO, MGNREGA, Jalpaiguri | Pending
7 | DPC0017 | 2016-06-30 | District | Sushil Kujur | & Others | Sylee Chel Line, Rungamattee TG | Rungamattee | Non-disbursement of wages | Forwarded to the PO & BDO, Mal vide Memo No. 1478/IV/2/MGNREGS dated 08-07-2016 of the DNO, MGNREGA, Jalpaiguri | Pending
8 | DPC0018 | 2016-05-10 | District | Pradip | Karjee | Dhondasimla, Angrabhasa, Jalpaiguri | Angrabhasa II | Irregularity in MGNREGA works | Forwarded to the PO & BDO, Nagrakata vide Memo No. 1477/IV/2/MGNREGS dated 08-07-2016 of the DNO, MGNREGA, Jalpaiguri | Pending
9 | DPC0019 | 2016-07-18 | District | Debraj | Sharma | Ambari TG, Chamurchi | Chamurchi | Irregularity in Tender process | Forwarded to PO & BDO, Dhupguri vide Memo No. 1514/IV/2/MGNREGS dated 20-07-2016 of the DNO, MGNREGA, Jalpaiguri | Pending
10 | DPC0020 | 2016-08-12 | District | Bishal | Oraon | Gandrapara TG, Banarhat | Banarhat I | Non - provision of work | Forwarded to the PO & BDO, Dhupguri vide Memo No. 1707/IV/2/MGNREGS dated 22-08-2016 of the ADPC & ADM, Jalpaiguri | As per the report submitted by the PO & BDO, Dhupguri vide Memo No. 854/NREGS/DHP dated 08-03-2017 "THE COMPLAINANT WAS PROVIDED JOB BUT HE DID NOT ATTEND AT THE WORKSITE"
11 | DPC0021 | 2016-09-07 | District | Asraful Alam | & Others | Part No. 15/164 & 165, Baroghoria GP | Baroghoria | Poor quality of work | Forwarded to the PO & BDO, Dhupguri vide Memo No. 1845/IV/2/MGNREGS dated 29-09-2016 of the ADPC & ADM, Jalpaiguri | Pending
12 | DPC0022 | 2016-09-29 | District | Nazir Md. | & Others | Nauya Para, Nagar Berubari | Nagar Berubari | Non-payment of wages | Forwarded to the PO & BDO, Sadar vide Memo No. 1848/IV/2/MGNREGS dated 29-09-2016 of the ADPC & ADM, Jalpaiguri | Pending
13 | DPC0023 | 2016-09-15 | District | Bidhan | Roy | Dharampur, Maynaguri | Dharmapur | Irregularity in MGNREGA work execution | Forwarded to the PO & BDO, Maynaguri vide Memo No. 1846/IV/2/MGNREGS dated 29-09-2016 of the ADPC & ADM, Jalpaiguri | Pending
14 | DPC0024 | 2016-09-07 | District | Asraful Alam | & Others | Part No. 15/164 & 15/165 Baroghoria | Baroghoria | Non-execution of scheme | Forwarded to the PO & BDO, Dhupguri vide Memo No. 1854/IV/2/MGNREGS dated 04-10-2016 of the ADPC & ADM, Jalpaiguri | Pradhan, Baroghoria GP has been directed to stop payment of the scheme vide AAP No. 0704032003185 (Construction of canal at the land of 2No. Ispat to Binsuti vide Memo No. 5324/NREGS/DHP dated 25-10-2016 of the
15 | DPC0025 | 2016-10-18 | District | Bigni Kujur | & Others | Nauya Para, Nagar Berubari | Nagar Berubari | Non-payment of wages | Forwarded to the PO & BDO, Sadar vide Memo No. 1882/IV/2/MGNREGS dated 21-10-2016 of the ADPC & ADM, Jalpaiguri | Pending
16 | DPC0026 | 2016-10-21 | District | Mahabul Alam | & Others | Magurmari, Dhupguri | Magurmari I | Non-payment of wages | Forwarded to the PO & BDO, Dhupguri vide Memo No. 1902/IV/2/MGNREGS dated 26-10-2016 of the ADPC & ADM, Jalpaiguri | as per the report submitted by the PO & BDO, Dhupguri vide Memo No. 853/NREGS/DHP dated 08-03-2017 "NO PAYMENT HAS YET BEEN MADE"
17 | DPC0027 | 2016-10-21 | District | Haripada Roy | & Others | Magurmari, Dhupguri | Magurmari I | Non-payment of wages | Forwarded to the PO & BDO, Dhupguri vide Memo No. 1901/IV/2/MGNREGS dated 26-10-2016 of the ADPC & ADM, Jalpaiguri | as per the report submitted by the PO & BDO, Dhupguri vide Memo No. 853/NREGS/DHP dated 08-03-2017 "NO PAYMENT HAS YET BEEN MADE"
18 | DPC0028 | 2016-10-21 | District | Rabindranath Roy | & Others | Magurmari, Dhupguri | Magurmari I | Irregularity in MGNREGA works | Forwarded to the PO & BDO, Dhupguri vide Memo No. 1900/IV/2/MGNREGS dated 26-10-2016 of the ADPC & ADM, Jalpaiguri | as per the report submitted by the PO & BDO, Dhupguri vide Memo No. 855/NREGS/DHP dated 08-03-2017 "NO RBM SCHEME WORK HAS BEEN TAKEN UP FROM MGNREGA"
19 | DPC0032 | 2016-11-03 | District | Bipul | Tarafdar | Uttar Gurudebpur, Dharmapur, Maynaguri | Madhabdanga-II | Non payment of bill amount against material supply | Forwarded to the PO & BDO, Maynaguri vide Memo No. 1935/IV/13/MGNREGS dated 09-11-2016 of the ADPC & ADM, Jalpaiguri | Prodhan, Madhabdanga II vide Memo No. 399/Mad-II/2017 dated 09-03-2017 has assured to clear the outstanding amount at the earliest possible.
20 | DPC0030 | 2016-10-27 | District | Sahid | Md. | Uttar Dhumpara, Angrabhasa | Angrabhasa II | Non-payment of wages | Forwarded to the PO & BDO, Nagrakata vide Memo No. 1938/IV/13/MGNREGS dated 09-11-2016 of the ADPC & ADM, Jalpaiguri | Pending
21 | DPC0031 | 2016-10-28 | District | Gyan Bdr Chhetri | & Others | Uttar Dhumpara, Nathuahat, Nagrakata | Angrabhasa II | Irregularity in MGNREGA works | Forwarded to the PO & BDO, Nagrakata vide Memo No. 1937/IV/13/MGNREGS dated 09-11-2016 of the ADPC & ADM, Jalpaiguri | Pending
22 | DPC0033 | 2016-11-30 | District | Khairul | Hoque | Sukhani, Rajganj | Sukhani | Irregularity in Tender Process | Forwarded to the PO & BDO, Rajganj vide Memo No. 2073/IV/13/MGNREGS dated 15-12-2016 of the ADPC & ADM, Jalpaiguri | Pending
23 | DPC0034 | 2017-01-20 | District | Smt. Srimati | Barman (Roy Pradhan) | Pradhan Para, PO Baroghoria, Dhupguri | Baroghoria | Irregularity in construction of AWC | Forwarded to the PO & BDO, Dhupguri vide Memo No. 130/IV/13/MGNREGS/Pt 3 dated 03-02-2017 with copy to the complainant | As per the report submitted by the PO & BDO, Dhupguri vide Memo No. 850/NREGS/DHP dated 08-03-2017 "THE WORK IS RUNNING AS PER THE SCHEDULE & ESTIMATE"
24 | DPC0035 | 2017-01-31 | District | Sri Pankaj | Dey | Dakshin Khagrabari, Maynaguri | Khagrabari I | Non-provision of wage employment | Forwarded to the PO & BDO, Maynaguri vide Memo No. 129/IV/13/MGNREGS/Pt 3 dated 03-02-2017 with copy to the complainant | Pending
25 | DPC0036 | 2017-02-21 | District | Anubala | Oraon | Sarkar Para, Sriram Para, Garalbari | Garalbari | Non - payment of un-skilled wages | Copy forwarded to the PO & BDO, Sadar vide Memo No. 219/IV/13/MGNREGS/Pt 3 dated 22-02-2017 with intimation to the complainant | Pending